## Slide 1: Lecture Construction scheduling and cost control

## Slide 2: Learning objectives
After completing this course, you’ll be able to:
Explain core concepts in construction scheduling and cost control
Describe how BIM tools support time and cost management
Create 4D construction simulations using Navisworks
Link model elements to schedule tasks in TimeLiner
View and manage project schedules using ACC
Track task progress and share schedule updates with project teams
Set up and manage budgets in Cost Management
Forecast project costs and monitor financial performance

## Slide 3: What is construction scheduling?
Every construction project is unique, involving multiple players, objectives, and constraints.
Each stakeholder has their own priorities and responsibilities.
Every project must balance three essential factors: scope, time, and cost.
A construction schedule brings order to this complexity.

## Slide 4: Key parts of a schedule
Activities: specific tasks such as pouring a slab, erecting steel, or installing drywall.
  Activities break a project into manageable units of work. Each activity carries assigned resources, such as crews, equipment, and key materials. Each activity has a duration
Relationships: logic interactions connecting connecting activities.
  Relationships can be Finish to Start, Start to Start, Start to Finish, Start to Finish
Milestones: specific points in time serving as checkpoints to measure overall progress.

## Slide 5: Key parts of a schedule
To keep all this organized, activities are structured within a Work Breakdown Structure, or WBS.
The WBS links project scope to schedule by organizing deliverables into work packages and tasks, creating a hierarchy that makes even the largest schedules easier to manage.

## Slide 6: Objectives and constraints
Objectives define what the project is trying to achieve:
  Minimizing costs
  Shortening duration
  Maintaining quality
  Balancing all three
Constraints define the boundaries in which the project must operate:
  Hard constraints
  Soft constraints

## Slide 7: Why scheduling matters?
Decision Making
Coordination
Risk Management
4D Scheduling
Managers can see where activities may clash, where resources may be overcommitted, and where delays in one task might impact the entire project.
Schedules align the work of subcontractors, suppliers, and trades so that activities happen in the right order and at the right time.
By tracking progress against the baseline, project teams can identify slippages early, evaluate their impact, and take corrective action before problems escalate.
4D simulations bring time and space together, making it easier to visualize how the project will unfold and where challenges might arise.

## Slide 8: What is a critical path?
The critical path is the longest path through the network of activities, measured in time.
If any activity on this path is delayed, the entire project will finish late, because there is no buffer built into these tasks.
This is why activities on the critical path are considered “zero float” tasks.

## Slide 9: Float and flexibility
Many schedules have a built-in buffer, known as float or slack.
Total float is the max amount of time that an activity can be pushed out without affecting the project finish date.
Free float is the amount of time an activity can be delayed without delaying the start of its immediate successor.

## Slide 10: Cost control system
A cost control system provides the framework for managing project finances in a structured and transparent way.
  Budget: represents the financial plan for the project. It is established at the start and sets the benchmark against which all costs will be measured.
  Commitments: represent the amounts formally tied up through contracts, subcontracts, or purchase orders. Even before money is spent, commitments show what funds are already obligated.
  Actual costs: show what has truly been spent as invoices are paid or labor hours are charged
  Forecast: shows the total expected cost at completion, combining what has already been spent with predictions for what is still to come

## Slide 11: Budget, cost, and schedule interaction
The S-curve plots cumulative spending over time.
  The budget curve shows how the budget was expected to be spent as activities move forward.
  The actual curve shows what has really been spent.
You had planned to be done with the steel package at the end of Month 8. However, today is the end of Month 8, and only 75% of the steel activity is completed. This shows that the project is behind schedule.
  Looking at the S-curve, you budgeted for $100,000 to be spent by the end of month 8; however, the actual cost ended up being $150,000. This shows your project is overbudget and that the steel package hasn’t been completed as planned.
  You were supposed to spend $150,000 by the end of Month 12; but given that you spent this money in Month 8; your project is about 4 months late.

## Slide 12: Scheduling with Navisworks
Navisworks enables planners and project teams to simulate construction sequences by linking model elements to a schedule.
Start by exporting the model from Revit and then append it to Navisworks to prepare it for scheduling.

## Slide 13: Navisworks file types

## Slide 14: Link model elements to schedule tasks
The Find Items window allows you to search for items with a common property or combination of properties.
The left pane contains the Find Selection Tree with a drop-down list at the top, allowing you to select the level of item to start searching at.
The right pane allows you to add conditions to find the qualifying items in your scene.
Save the results in search sets to be converted to construction tasks.

## Slide 15: Simulate and compare planned vs. actual progress
Use 4D simulations to compare the planned sequence with actual construction progress.
Update task durations to visualize differences and identify schedule risks.

## Slide 16: Scheduling with the Autodesk Construction Cloud
In Autodesk Construction Cloud, scheduling becomes a collaborative process, where the entire team can access and understand project timelines in real time.

## Slide 17: Create and manage plans
In the Schedule tool, plans can be created as standalone plans to manage one-off projects, or as connected plans ideal for tasks that follow a set pattern.
Start by setting up the calendar, the WBS, and then build the series of tasks either independently or as part of an activity.

## Slide 18: Track and update schedule progress
Construction projects are constantly changing, and a schedule that isn’t updated quickly becomes unreliable.
Keeping schedules and plans current in ACC ensures the entire team is working from the same information, making it easier to track progress, respond to delays, and keep the project on course.

## Slide 19: Cost control with Cost Management
Cost Management in ACC centralizes project budgeting, contracts, and financial change control in a cloud environment.
You can set up budgets, manage committed costs, track actual costs, and monitor forecasted costs.

## Slide 20: Manage committed costs
In Cost Management, you can use the Cost tool to create contracts with subcontractors.
These contracts and purchase orders reflect in the committed costs columns.

## Slide 21: Manage payment applications
A Budget Payment Application is part of the main contract. It is used for the contractor to get paid by the owner. This is known as an upstream payment.
A Cost Payment Application is part of the contract with subcontractors. It is used for the contractor to pay subcontractors. This is known as downstream payment.

## Slide 22: Forecast project costs
In ACC, Forecast projects future costs based on current commitments, pending changes, and expected trends.
As the project progresses, more activities are happening, which means more cost payment applications are paid to subcontractors, and more budget payment applications are submitted to the owner.
These payment applications might include changes compared to the original budget and schedule. That’s why forecast costs are an essential part of any cost control system to make sure your project stays within budget and on time.