## Slide 1: Lecture Preconstruction management

## Slide 2: Learning objectives
After completing this course, you’ll be able to:
Explain why preconstruction management matters and how a BIM Execution Plan (BEP) defines BIM uses, roles, information exchanges, naming conventions, and shared coordinates.
Set up projects and organize documents in Autodesk Construction Cloud to support coordination, traceability, and decision-making.
Federate multidisciplinary models in ACC and prepare saved views to support coordination reviews.
Review constructability using Model Coordination, group clashes, and manage Issues to resolution.
Build and interpret a high-level cash-flow model tied to schedule milestones and subcontractor commitments.
Assemble bid packages, translate bid results into contract scope, and support collaborative contract review and award.

## Slide 3: What is preconstruction?
Define the project
Identify
Risk
Value
Engineering
Define
Scopes
Procure
Materials
Scheduling
Estimate
Costs
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.

## Slide 4: Stakeholders involved in preconstruction
Client: defines the project goals, desired budget, and overall vision while making key decisions throughout preconstruction.
Architect: develops the design and BIM and ensures it aligns with the client’s vision, regulations, and functional requirements.
Engineer: provides technical designs and calculations to ensure the project’s systems are safe and feasible.
Contractor: contributes cost estimates, schedules, and constructability reviews to optimize the project’s efficiency and budget.
Subcontractor: offers trade-specific expertise, pricing, labor, and input on materials and construction methods.
Consultant: delivers specialized services such as BIM, permitting support, or value engineering.
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.

## Slide 5: The preconstruction process
Goals
Scope
Site
Analysis
BIM
Budget & Schedule
Bidding
Procurement
Permitting
Initial Meeting
Recurring Meetings
Construction Begins
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.

## Slide 6: What is BIM?
Building Information Modeling (BIM) is the PROCESS of delivering and operating built assets using well organized digital information collaboratively.
This standardization is what allows different teams to work together.
The process follows standards such as the ISO 19650.
Notes: At the heart of BIM is the 3D model, a visual representation of the project. But it's not just any 3D model. Each element within the model is packed with data, dimensions, material, and more. This information is crucial for creating accurate construction drawings, reducing errors and keeping the project on track. So how does all this digital information translate in the real-world construction process?

## Slide 7: The BIM execution plan (BEP)
A BIM Execution Plan (BEP) is a comprehensive guide that outlines how Building Information Modeling will be implemented throughout a project.
Components may include the following:
Project information and scope
Project stakeholders
Roles and responsibilities
Project and data requirements
Standards and protocols
Deliverables and level of development
Collaboration and coordination strategies
Quality control and validation
Schedule and milestones
Data security and ownership
Risk management
Training and support
Handover/post-construction guidelines

## Slide 8: Naming standards
Standardized processes like naming files makes it easier for people to find and use the information quickly.
The file name structure for this course’s project is:
  Project
  Originator
  Functional Breakdown
  Spatial Breakdown
  Form
  Discipline
  Number

## Slide 9: Naming standards
Names of files should be made from the list as shown in the BEP.
PRJ001-ARC-XX-ZZ-M3-A-0001.rvt
PRJ001: The unique code for this project
ARC: This file was created by the Architecture company
XX: No volumes in the project
ZZ: Contains all / multiple volumes of the project
M3: Native 3D model (such as Revit project model)
A: The file relates to the architecture (walls, windows doors etc.)
0001: First time the preceding 6 fields have been used in a name

## Slide 10: Naming standards
Names of files should be made from the list as shown in the BEP.
PRJ001-LAN-XX-ZZ-M3-L-0001
PRJ001: The unique code for this project
LAN: This file was created by the Landscape Company
XX: Contains no volumes
ZZ: Contains multiple levels
M3: The document type is a native 3D model file
L: The file relates to the Landscape Architect role.
0001: First time the preceding 6 fields have been used in a name

## Slide 11: What is ACC?
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Single source of truth for every project, from design through handover on one data platform.
Streamlines end-to-end construction workflows: design, coordination, field, and turnover.
Project stakeholders collaborate in the cloud on ACC during preconstruction to eliminate duplicate effort by streamlining communication.

## Slide 12: Common Data Environment Folder set-up
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.

## Slide 13: BIM coordination in ACC
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Align 3D models from all disciplines.
Resolve spatial conflicts before construction begins.
Prevent rework, delays, and hazards.
Collaborate on a single model in the cloud.
Assess constructability.

## Slide 14: Analyzing constructability
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Can it be built?
How best to do it?
What will it cost?

## Slide 15: Constructability review using BIM
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Key elements of constructability:
Design practicality and buildability.
Construction methods.
Alignment of the design and construction schedule.
Material availability and compatibility.
Site constraints and existing conditions.
Common preconstruction issues:
Incomplete design.
Poor model coordination.
Incorrect model alignment.

## Slide 16: The constructability review process
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Review clash detection results & resolve conflicts.
Use filters & views to analyze whether the design is practical and feasible.
Review Issues logs to resolve issues or collaborate with designers.
Ask key constructability questions.
Document a report & meet with stakeholders to move forward with the project.

## Slide 17: Contents of a bid package
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Cover Letter
Instructions
Submit the complete bid proposal including the attached bid form and all requested documentation by May 1, 2026, via Sunbelt@autodesk.com.
Ensure pricing reflects the full scope of work as defined in the bid package.
Key Dates
Invitation Issued:
RFI Deadline:
Bid Due Date:
Award Date:
Contact Information
Email: Sunbelt@autodesk.com
Address: 354 Sunbelt Drive Miami, FL
Scope of Work
Concrete
The concrete subcontractor shall provide all labor, materials, equipment, and supervision to complete the concrete work as specified in the project documents. This includes, but is not limited to:
Installing cast-in-place concretes for foundations and slabs.
Placing reinforcing steel and embeds.
Performing formwork, curing, and protection of concrete surfaces.
Coordination with other trades for placement of sleeves and embedded items.
Providing mockups and quality control.
Cleaning and demobilizing upon completion of work.
Drawings and Specifications
Bid Form
Project Name:
Bidder (Company Name):
Contact Name & Title:
Phone / Email:
Scope of Work: Concrete, cast-in-place
Unit: CY
Quantity: 200
Unit Price: $_______
Total Price: $_______
Subtotal: $____________
Bond Allowance: $__________
Total Bid Amount:
By signing below, the bidder confirms they understand the scope of work and agree to complete it as specified.
Signature: ______________________________
General and Supplementary Conditions
These are the standard contractual requirements that apply to all subcontractors including:
Project Schedule
Site Access and Safety
Payment Terms
Submittals and Approvals
Change Orders
These are project-specific modifications or additions to the General Conditions such as:
Work Hours:
Environmental Requirements:
Insurance and Bonding:
Coordination:
Penalties:
Schedule
Safety, Quality, and Insurance Requirements
All personnel must comply with OSHA regulations and project-specific safety protocols. PPE must be worn at all times. Subcontractors must submit a site-specific safety plan before starting work.
Work must comply with project drawings, specifications, and building codes. Defective work must be corrected at the subcontractor’s expense. Submittals must be reviewed and approved prior to installation.
Subcontractors must maintain the following coverage during the project:
General Liability
Worker’s Compensation
Automobile Liability

## Slide 18: Subcontractor bid packages
Bid packaging ensures all subcontractors receive the same information, at the same time, with clear instructions and expectations.
By clearly defining the scope, schedule, quality standards, and contractual requirements upfront, bid packages reduce the chance of misunderstandings, scope gaps, and change orders.
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.

## Slide 19: The subcontractor bid packaging process
Draft, coordinate, & finalize documents
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Upload to ACC
Assign subcontractors permissions to their bid package folder in ACC
Subcontractors prepare bids
Upload to ACC
General contractor reviews bids
Award subcontractor(s)

## Slide 20: Subcontractor contract types
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Fixed price/ Lump Sum: general and subcontractors agree on total price for the project before it starts.
Cost-plus: general contractor agrees to pay the subcontractor for actual costs plus a fee or percentage for overhead and profit.
Time and materials: general contractor agrees to pay hourly rates for labor and actual costs, sometimes with a markup.
Unit price: project is broken down into units of work, and the general contractor agrees on a price for each unit.
Guaranteed maximum price: subcontractor agrees that the total cost will not exceed a certain amount.

## Slide 21: Schedule of values in preconstruction
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Z
2,222,452.93

## Slide 22: Cost timing in construction
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Time
Cost
Costs rise and fall depending on the stage of work.
Timing of work influences cost timing.
General contractors often spend money before they receive payment
Pay subcontractors
Receive payment
Project End
Project Start
Cash flow out
Cash flow in

## Slide 23: Benefits of cash flow analysis
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Cash flow analysis forecasts the movement of money in and out of a project over a period of time. It allows you to:
Anticipate financial risks.
Ensure funds are available.
Keep the project schedule on track.
The availability of cash informs procurement, labor, and construction activity scheduling. It helps:
Avoid delays caused by underestimations.
Keep project costs accurate.

## Slide 24: What is permitting in preconstruction?
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
AHJ = Authority having jurisdiction

## Slide 25: Types of permits
Autodesk Confidential & Proprietary Information - Please do not post, copy or distribute without authorization.
Building: structure complies with local building codes, safety standards, and accessibility requirements.
Zoning: project complies with local land use regulations and municipal zoning codes.
Environmental: project does not pose threat to natural resources, air or water quality, or protected land.
Specialty: specialized installations meet safety codes and regulatory standards.
Occupancy: project was built according to the approved plans and is safe.

## Slide 26: The permitting submittal process
Drawings, details, and estimated value.
AHJ conducts a plan check.
AHJ approves permit.
Early submission ensures on-schedule construction.
AHJ may issue plan check comments requiring revisions.