Exercise duration: ~20 minutes

Practice exercise – Answer Key

- Manage project costs in Cost Management

- The following steps were completed in the videos for Module 3: Cost control with Forma Cost Management. If you followed along in the videos, you are ready to start the exercise that follows these steps. If you have not already performed these steps, make sure to complete them first:

- You activated Cost Management using freeform code in the Learn Build project you were invited to by your instructor on Autodesk Forma for Construction.

- In the Settings page of Cost Management, in the General tab, under Budget and Contract allocation, you selected Multiple budgets to one Contract.

- In the Settings page of Cost Management, in the General tab, under Retention, you assigned 10% for the Budget Payment Application and the Cost Payment Application.

- In the Settings page of Cost Management, in the Budget tab, you created a sample segment for the Code and imported the codes using the Code List.xlsx file in the dataset folder.

- In the Settings page of Cost Management, in the Budget tab, you created a sample segment for the Levels and imported the levels using the Levels.xlsx file in the dataset folder.

- In the Budget tool, you uploaded the budget using the Project Budget.xlsx file in the dataset folder.

- In the Budget tool, you created a Main Contract with the Owner.

- You modified the dates of the contract to Start on September 1, 2026 and end on December 25, 2026 and created weekly billing periods.

- In the Budget tab, you created a main contract schedule of values from all the budget lines.

- You created a contract with the concrete subcontractor based on Division 03 line items.

- In the details of this contract, under Manage Billing Periods, you clicked Inherit from Master Schedule.

- You created a contract with the steel subcontractor based on Division 05 line items and specified the correct billing periods using the same approach as the concrete contract.

- In the Forecast tool, you added a reference to the schedule in Build, and linked each activity to its corresponding budget line item.

- Once these steps are completed, you will be ready to start the exercise. You will configure Cost Management, work with budgets and payment applications, and forecast project costs.

Learning objectives:

By the end of this exercise, you should be able to:

- Create and manage payment applications.

- Forecast project costs using budget and schedule information.

Success criteria:

- Project budgets and cost items are created or imported correctly.

- Payment applications are created and linked to the project budget.

- Project costs are forecasted using current budget information.

- Exercise questions are completed and required items are submitted for review.

- Follow the steps below to complete this practice exercise. Create a cost payment application for the steel subcontractor for the billing period of Nov 1, 2026 – Nov 7, 2026. In this payment application, 100% of the work was completed for these activities: Second Floor Columns, Third Floor Columns, Second Floor Framing. The Second Floor Framing has an extra $1,000 cost associated with it. Set this application as paid. - What is the total percent completion on the contract with the steel subcontractor? - __________________________________________________________________ - Answer Key - The percent completion is 37.5%. Check the work of the student on Autodesk Forma for Construction Cost Management. Complete the following steps: - For the same billing period, create a budget payment application. - In the associate costs, add the completed cost payment application you created in the previous step, then aggregate the costs. - Set the budget payment application as paid. - What is the remaining balance on the contract with the owner? - __________________________________________________________________ - Answer Key - The remaining balance is $9,800. Complete the following steps: - In the Forecast tab, create one distribution item for the three activities you included in the cost payment application. - Distribute their cost over their respective start and end dates using a front-loaded curve. - Look at the cash flow analysis chart, for the week ending in Nov 6, 2026, what are the values of the cumulative work completed and the cumulative actual cost? Why are they different. - __________________________________________________________________ - Answer Key - The cumulative work completed is $3,700 and the cumulative actual cost is $3,300. The difference is $370 which is equal to the retainage.