Exercise duration: ~15 minutes

Practice exercise – Answer Key

# Calculate direct costs in Estimate

- The following steps should be completed in Practice exercise: Measure quantities in Takeoff. If you completed that exercise, you are ready to start this exercise. If not, make sure these steps are completed:

- In the Setting menu of Takeoff, you specified a measurement system and uploaded the Project Level Classification.xlsx into the Classification system 1.

- In the Setting menu of Takeoff, you specified the correct currency and time frame conversions.

- In the Setting menu of Takeoff, you created at least one output definition, for example, an output definition for Window Type A.

- In the Sheets & Models tool:

  - You uploaded the Architectural Model.rvt file from the Version 1 folder in the dataset folder to the 3D Models tab.

  - You uploaded the Architectural Sheets.pdf and Structural Sheets.pdf files from the Version 1 folder in the dataset folder to 2D Sheets tab and extracted the correct sheet names and numbers.

- You created a new takeoff package named Practice Exercise 2.

- You found the following quantities using BIM-based takeoff types and newly created output definitions,

  - Number of single flush wooden doors and their frames.

  - Number of ceiling tiles.

  - Number of gypsum wall boards.

- You found quantity of cast in place concrete in spread footing F1 using area-based takeoffs on sheet S103 and the concrete line item from the hub library.

Once these steps are completed, you will be ready to start the exercise. You will apply the skills learned in this module to transfer quantities from Takeoff into Estimate and develop project cost information. You will organize estimate data, apply unit costs, calculate direct costs, and add markups while answering the questions provided.

Learning objectives:

By the end of this exercise, you should be able to:

Transfer quantities from Takeoff to Estimate.

Organize estimate items and customize cost fields.

Apply unit costs to estimate items.

Calculate direct costs.

Success criteria:

Quantities are successfully transferred from Takeoff to Estimate.

Estimate items and cost fields are configured correctly.

Unit costs are applied to estimate items to calculate direct costs.

Exercise questions are completed and answers are submitted for review.

- In Takeoff, open the inventory and send the five quantities you found in the previous exercise, Practice exercise: Measure quantities in Takeoff, to Estimate. In Estimate, apply the appropriate grouping properties to see the quantity of concrete in spread footings. - What is the labor cost for Footing F1? - __________________________________________________________________ - Answer Key - The labor cost is $3,008.61 The contractor will hire a subcontractor to complete division 9 who charge $50 per GWB and $10 per ACT. What is the total cost of Division 9. - __________________________________________________________________ - Answer Key - The total cost of Division 9 is $ 45,110.32. In Estimate, add a filter to show line items with total costs greater than $50,000. - How many line items have a total cost greater than $50,000. - __________________________________________________________________ - Answer Key - There are five line items with total costs greater than $50,000, Shear Walls, SOG, Upper Floors, CMU, and brick. Instead of hiring a subcontractor, the contractor decided to self-perform the brick line item. Each brick costs $0.3 and the productivity for labor and equipment is 800 bricks per hour. Using the mason labor and the scaffolding equipment from the hub library, what it the new total cost of brick? - __________________________________________________________________ - Answer Key - The new total cost of brick is $76,494.62. Export your final estimate and submit as part of your answer to this exercise. - __________________________________________________________________ - Answer Key - The students should submit an Excel sheet for this question.